## Event RA
Risk Assessment
Event |  |  | Torpids 2019 |  |  | Date: |  | 27/2/2019 - 2/3/2019
Author |  |  | Keir Bowater |  |  | Rev: |  | 2019-02-03
No: | Hazard | Reduce probability a Hazard causing a Hazardous Event |  | Hazardous Event | Reduce the Severity of Harm |  | Harm | Severity (1-5) | Probability (A-E) | Level of Risk (L/M/S/I) | Action Owners
|  | Barriers | Action to maintain barriers |  | Controls | Action to maintain controls |  |  |  |  | Race Secretary | Race Committee | Incident Co-Ordinator | Launch Drivers | Senior Umpire | Marshals | Other | if other, who?
Water
1 | Incompetent crews | Coaches and crews are expected to have read the Safety Briefing and circulation plan before going afloat for practice or racing. Marshals to check all boats for adequate buoyancy measures before boating. Crews and coxes are expected to be suitably competent and may be removed from the water if not. Races are stopped if necessary to avoid harm to crews. | Prepare and provide safety briefing and inform captains that their crews and coaches must read it. Marshals briefed on boat checks. | Capsize or sinking during a race | Rescue with launch Administer first aid Warm any casualties up slowly | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Cold water immersion leading to mild hypothermia | 2 | C | Low | X | X |  | X |  | X | X | Coaches, coxswains, crews
1 | Circulation conflict | Crews are expected to be aware of and follow circulation plan. Crews and coxes are expected to be suitably competent and may be removed from the water if not. Marshals to direct crews, and briefed to klaxon in case of imminent collision, causing all boats to stop. | Prepare and provide safety briefing and inform captains that their coaches and crews must read it. Race Committee/Secretary/marshals to remain vigilant for incorrect circulation and communicate to crews circulating incorrectly. OURCs registered and briefed coxes only. | Collision with bank or a non-racing boat. | Rescue with launch. Marshals briefed to klaxon if collision occurs, stopping other boats and preventing other boats also colliding | A fully equipped rescue launch in attendance for all divisions, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Damage to boats Injury to crews. Cold water immersion leading to mild hypothermia | 2 | C | Low | X | X |  | X |  | X | X | Crews, coxswains, coaches
2 | Heel restraints broken or too loose, bow balls not correctly fitted, backstays not fitted, hatch covers not present if needed | Boat checks to be conducted by marshals and crews | Ensure that marshals checking equipment have instructions and a checklist | Rower trapped in capsized boat, collision made dangerous by unsafe or malfunctioning equipment | Rescue with launch | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Water aspiration, drowning | 3 | B | Low |  |  |  | X |  | X | X | Crews, coxswains, coaches
3 | Cox wearing incorrect or poorly fitted lifejacket | Coxes to fit lifejackets correctly | Instructions to competitors. Correct use of lifejacket part of (required) OURCs coxing briefing. Exempted coxes must read the presentation. Marshals briefed to check lifejackets before allowing any crew to boat. | Cox unable to use lifejacket when needed | Rescue with launch | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Water aspiration, drowning | 3 | B | Low | [5 empty] | X | X | Coxswains, crews
4 | Athletes who are unable to swim being present in racing crews | All participants must have passed an Oxford University standard swim test within the prevoius six years.\ | Entries system prevents college crews with non-swim-tested crews being entered for racing. Committee to maintain vigilance on athletes with out-of-date swim tests. | Athletes who are unable to swim falling into deep water | Rescue with launch | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Water aspiration, drowning | 4 | A | Low | X |  |  | X |  |  | X | Club secretaries
5 | Poorly maintained equipment | Captains must ensure their equipment is satisfactory | Captains and coxes reminded to check equipment before racing | Equipment failure possible capsize | Rescue with launch Administer first aid Warm any casualties up slowly | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Damaged equipment Mild hypothermia Injuries caused by equipment failure | 3 | B | Low |  |  |  | X |  | X | X | Coxswains, crews
6 | Safety Launch | All launch drivers to be RYA2 trained. Lifejackets worn by everyone, kill cord worn by the driver at all times. | Secretary and Sabbatical Officer to check that all drivers are trained. Refresher training considered if necessary. | Capsize | Second launch available to assist. Rescue with launch Administer first aid Warm any casualties up slowly | Secretary and Sabbatical Officer to check that a second launch is available at all times. | Cold water immersion leading to mild hypothermia | 2 | B | Low |  | X |  | X
6 | Safety Launch | Lifejackets worn by everyone, kill cord worn by the driver at all times. | A reminder of life jackets and killcords to be given to all launch drivers | Falling Out | Rescue with launch Administer first aid Warm any casualties up slowly | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Cold water immersion leading to mild hypothermia | 2 | C | Low |  | X |  | X |  |  | X | All launch passengers
7 | Poor launch driving | All launch drivers to be RYA2 trained | Secretary and Sabbatical Officer to check that all drivers are trained. Refresher training considered if necessary. | Capsize Falling out of aunch | Lifejackets worn by everyone on launch, kill cord worn by the driver at all times. | A reminder of life jackets and killcords to be given to all launch drivers | Cold water immersion leading to mild hypothermia | 3 | B | Low |  | X |  | X
Weather
1 | Possibility of electrical storm | All crews to leave the water or seek shelter as soon as possible, on instruction from Senior Umpire communicated around race course by radio and tannoy. The 30/30 rule to be used for thunder/lightning. | Ensure that coxes, marshals and umpires are adequately briefed. Inform captains they are expected to brief crews and coaches. | Rower or official struck by lightning | Provisions for first aid, medical treatment, and casualty evacuation to hospital. AEDs mounted on University BH, and upstream side of Balliol BH. | Ensure that first aiders, etc., are competent and properly equipped. | Electrical burns, shock | 3 | B | Low | X |  |  |  | X
2 | Bad weather causing un-rowable and/or dangerous conditions | Modified flag system to be followed (see below) | Weather and stream to be monitored by Senior Umpire in consultation with EA and other advisors. | Crews swept into obstacles. | A fully equipped rescue launch in attendance for every division, and at hand during warming-up | Ensure that there is sufficient safety cover. Check equipment prior to use. | Equipment damage Rowers injured Cold water immersion leading to mild hypothermia | 2 | D | Moderate | X | X |  | X | X |  | X
2 | Bad weather causing un-rowable and/or dangerous conditions | Cancellation or restrictions to be implemented if appropriate. | Weather and stream to be monitored by Senior Umpire in consultation with EA and other advisors. | Boats capsizing or swamping | Rescue with launch Administer first aid Warm any casualties up slowly | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Cold water immersion leading to mild hypothermia | 3 | B | Low | X |  |  | X | X
3 | Low Visibility | Use adequate lighting on boats. If visibility is reduced to less than 100m on any part of the racing course then racing is suspended or cancelled at the Senior Umpire's discretion. | Senior Umpire to monitor conditions. All crews in last two divisions of the day to have lights on. Crews to be warned before the race if low visibility is likely to occur | Crews crashing into obstacles or other boats or other river users | Rescue with launch Administer first aid Warm any casualties up slowly | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Equipment damage Rowers injured Cold water immersion leading to mild hypothermia | 3 | B | Low | X | X |  | X | X |  | X | Coxswains, crews, coaches
4 | Icy Conditions | Safety launches used to clear small quantities of ice from the racing course. Racing cancelled at Senior Umpire's discretion if launches cannot sufficiently clear the race course of ice. | Senior Umpire to monitor weather conditions, helped by the race committee and marshals. | Boats collide with ice in the water | Rescue with launch If necessary. Use launch to escort damaged boats to closest landing stage. | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Damage to boats | 3 | B | Low | X | X |  | X | X | X
5 | Significant ice or lying snow on towpath | Change to coxes who do not need bankriders. | Senior Umpire to monitor conditions with the help of the Race Committee and make decision | Slipping on ice Cyclist collides with bystander, Cyclist or fixed object | Clearance of ice/snow possible, and/or move to static umpires (if racing on a Saturday). Administer first aid | Race Committee to clear snow/ice and/or grit if necessary. Provide adequate first aid cover. | Injury from slipping or collision | 2 | B | Low | X |  |  |  |  | X | X | Bankriders
6 | Extreme cold | Senior Umpires to use all available information to determine if it is safe to run racing. Measures taken by the Senior Umpires and Race Committee to maintain safety of marshals if necessary. Marshals and umpires encouraged to wear appropriate clothing and take other measures to ensure they are prepared for the conditions. Partial or full cancellation of racing at Senior Umpire discretion if conditions dictate. | Senior Umpires to monitor conditions with the help of the Race Committee and marshals. | Athletes becoming extremely cold whilst on the water | Administer first aid Warm any casualties up slowly | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Potential for Race Committee to install facilities for heating/hot drinks at Race Desk. | Mild hypothermia Injuries due to cold muscles before racing | 3 | B | Low | X | X |  |  | X
6 | Extreme cold | Senior Umpires to use all available information to determine if it is safe to run racing. Measures taken by the Senior Umpires and Race Committee to maintain safety of marshals if necessary. Marshals and umpires encouraged to wear appropriate clothing and take other measures to ensure they are prepared for the conditions. Partial or full cancellation of racing at Senior Umpire discretion if conditions dictate. | Senior Umpires to monitor conditions with the help of the Race Committee and marshals, and make decision. | Marshals or umpires becoming extremely cold | Administer first aid Warm any casualties up slowly | If conditions make it necessary, welfare team set up by the Race Committee to monitor condition of marshals. Heating measures considered at key points on the towpath. Potential for Race Committee to install facilities for heating/hot drinks at Race Desk. Provide adequate first aid cover | Mild/moderate hypothermia Marshals becoming ineffective leading to slow response to dangerous racing event | 3 | C | Moderate | X | X |  |  | X | X | X | Bankriders, umpires, welfare team
Other water users
1 | Other River traffic | Signs visible to river traffic displayed at the entry points onto the course .Senior Umpire to check river is clear using marshals, and ensure other river users on the racing course are static before starting racing. Marshals to make sure crews stick to the sides of the river, as shown by the circulation pattern leaving the centre free. Ensure crews do not spin in front of cruisers. Moor cruisers up when a race is about to go off. Coxes observe the circulation pattern and do not spin in front of cruisers. Racing to be stopped by marshals if river traffic seems likely to cause a hazard to racing crews. | Coordinating Senior Umpire makes contact before the event with other regular river users alerting them to the event (see event plan). Install signs displayed at the entry points onto the course. Brief marshals to make sure crews stick to the sides of the river, as shown by the circulation pattern leaving the centre free. Also not to allow crews to spin in front of cruisers. Key marshals equipped with megaphones to hail crews, and all marshals to communicate with other river users entering the course. Crreate holding points to moor cruisers up at when a race is about to go off. Brief coxes to observe the circulation pattern and not to spin in front of cruisers. | Collison between a crew and another river user | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. | Ensure that there is sufficient safety cover. Check equipment prior to use. | Cold water immersion leading to mild hypothermia | 3 | C | Moderate | X | X |  |  | X | X | X | Coxswains, other river users
Local Environment
1 | Objects in the river | Move any small object in the river that can cause an obstruction, using the launches if necessary. Protect the crews from larger, immovable, objects or suspend racing while they are moved. | Senior Umpire consider course inspection before opening course. Race officials and marshals to remain vigilant for new objects entering | Collision wth objects, Capsize | Rescue with launch If necessary. Use launch to escort damaged boats to closest landing stage. | A fully equipped rescue launch in attendance for every division, and at hand during warming-up. Ensure that there is sufficient safety cover. Check equipment prior to use. | Damage to boats, cold water immersion leading to mild hypothermia | 3 | B | Low | X | X |  | X |  | X
Handling boats on land
1 | Boats being moved on the land | Crews recommended to lift with a straight back and use good technique. Captains to be advised their coxes should monitor safe technique | Clubs aware of responsibilities for any supporters and spectators | Collision between boats or blades and spectator | Administer first aid | Ensure adequate Medical Cover present Marshals available at boathouses with radios to contact medical cover. | Injury to bystanders, cold water immersion leading to mild hypothermia | 2 | C | Low | [5 empty] | X | X | Coxswains, crews
Faulty, incorrectly set and poorly maintained equipment
1 | Debris in river | Move any small object in the river that can cause an obstruction, using the launches if necessary. Protect the crews from larger, immovable, objects or suspend racing while they are moved. | All launch users to be vigilant for debris in river | Failure of engine due to fouling of propeller | Rescue with another launch Remove debris from propeller | Launch to carry relevant British Rowing recommended safety equipment, including a knife and paddle. | Damage to launch | 2 | B | Low |  |  |  | X |  |  | X | All launch passengers
2 | Poorly maintained launch | Launch to be serviced regularly. | All launch users to be vigilant of any abnormal launch behaviour, and report it. | Mechanical failure | Racing to be suspended by the Senior Umpire until minimum number of operational launches achieved (2) | Race Committee to advise Senior Umpire immediately if number of launches drops below the minimum operational level. | Damage to launch | 2 | B | Low |  |  |  | X |  |  | X | All launch passengers
Pre-existing health conditions and low levels of fitness
1 | Strenuous exercise | Rowers should warm up on land and warm down and stretch. Advise captains that they and their coaches should take into account medical history when selecting crews, and that rowers should not compete if they feel unwell or are injured | Captains should be advised to brief competitors | Over-exertion | Marshal contacts Race Desk, who summons launch to assist if necessary and alerts First Aid by radio. Administer first aid | Ensure that marshals are properly briefed and equipped and that there is medical cover | Hyperventilation, pulled muscles, cramp, back injury | 1 | D | Low | X |  |  |  |  | X | X | Coxswains, crews, coaches, captains
2 | Pre-existing health conditions | Crew members are responsible for carrying their own medication if required (e.g. inhaler) | Captains should be advised to brief competitors | Collapse of athlete on land or water while not racing (e.g., asthma attack or serious fall) | Marshal contacts Race Desk, who summons launch to assist if necessary and alerts First Aid by radio. Administer first aid | Ensure that marshals are properly briefed and equipped and that there is medical cover | Serious health implications for competitor | 3 | B | Low | X |  |  |  |  | X | X | Coxswains, crews, coaches, captains
3 | Pre-existing health conditions | Crew members are responsible for carrying their own medication if required (e.g. inhaler) | Captains should be advised to brief competitors | Collapse of athlete during a race (e.g., asthma attack) | Marshal contacts Race Desk, who summons launch to assist if necessary and alerts First Aid by radio. Administer first aid | Ensure that marshals are properly briefed and equipped and that there is medical cover | Serious health implications for competitor | 3 | C | Moderate | X |  |  |  |  | X | X | Coxswains, crews, coaches, captains
Other
1 | Bankriders | Attendence at a bankrider briefing within the last 18 months mandatory for anyone who bank rides a crew Bankriders to keep a good lookout at all times | Bankrider briefings expire after 18 months and need renewing | Collision involving accompanying cyclists | Marshal contacts Race Desk, who summons launch to assist if necessary and alerts First Aid by radio. Administer first aid | Ensure that marshals are properly briefed and equipped and that there is medical cover | Injury to cyclists and pedestrians, possibly immersion | 1 | D | Low | X |  |  |  |  | X | X | Bankriders
1 | Cannon | Cannons locked up when publicly visible and supervised by Senior Umpires at all times. Cannons operated by a competent person, under the supervision of a firearms license holder. Cannons are unloaded when not required for immediate use. Operator is in immediate attendance to any loaded cannon. Cannon operator has a race radio, and is familiar with cannon use during racing. Spare cartridges are kept in a locked box, with keys removed. | Cannons supervised by Senior Umpires at all times. | Cannon discharge at inappropriate time Unauthorised access to or operation of the start cannon Theft of cannons | In case of a false firing leading to a false start of a race, Senior Umpires can communicate with marshals and klaxon to stop all crews if necessary. Clear plan of when cannon is fired normally is part of marshal briefing, to identify any false firing. Only blank cartridges are used. | Senior Umpire has radio in order to communicate with all marshals and other officials quickly. | Confusion of racing crews leading to false starts Breach of firearms legislation Crews racing into stationary crews who have not started or attached. Injury or accident to operator or passers-by | 3 | A | Low |  |  |  |  | X | X | X | Firearms License Holder
In the event of the Environment Agency (EA) displaying Amber or Red Boards at the local locks which indicates a strong stream, OURCs have developed a range of contingency plans to allow the Regattas to continue in some form. (In italics is the Flag state relating to the number of bucks drawn, which dictates what rowing takes place during training)
| Controls in place to reduce risks |  |  |  | Persons responsible for ensuring controls in place
| Blue Flag (2-3 bucks) Good conditions (high water, but low stream and wind): Full Programme Poor conditions (eg high stream or winds, but also possibly in very cold weather): Senior Umpire to consider whether safety measures are needed using all sources of available information and in discussion with the Race Secretary. Safety measures may include moving bunglines upstream, restricting coxes, moving to half-divisions, extra launches or a mix of measures. Crews may be permitted to withdraw with no financial penalty at the discretion of the Race Secretary. Curry contingency timetables to be used. |  |  |  | Senior Umpire with the help of the Race Committee, Race Secretary and Sabbatical Officer
Amber flag (4 bucks) Senior Umpire to consider what safety measures are needed using all sources of available information and in discussion with the Race Secretary. Safety measures may include moving bunglines upstream, restricting coxes, moving to half-divisions, extra launches or a mix of measures. Cancellation may be required. Novice coxes are highly unlikely to be used in most amber flag conditions. Crews may be permitted to withdraw with no financial penalty at the discretion of the Race Secretary. Curry contingency timetables to be used.
Red Flag (5+ bucks) Senior Umpire to consider what safety measures are needed using all sources of available information and in discussion with the Race Secretary. Safety measures may include moving bunglines upstream, restricting coxes, moving to half-divisions, extra launches or a mix of measures. Cancellation may be required. Red flag is highly likely to lead to half-divisions and S or X/S coxes only. Crews may be permitted to withdraw with no financial penalty at the discretion of the Race Secretary. Curry contingency timetables to be used.
Note on I5: 1 = Slight Injury or health effect that requires little or no treatment, and has no potential for time off rowing or training. OR Minor damage to equipment (<£100) 2 = Minor Injury or health effect that requires First Aid treatment or rest only and has a potential for a few days off rowing or training. OR Low damage repair costs (>£500) 3 = Moderate Injury or health effect that requires treatment beyond simple First Aid and potential for a week or so off rowing or training. OR High damage repair costs (>£1000) 4 = Major Injury or health effect that requires hospital treatment for more than one day and potential for a few weeks off rowing or training. OR Very high damage repair costs (loss of boat, 3rd party damage) 5 = Fatality or life threatening injury or health effect that could end a rowing career OR Major damage & major costs (loss of several boats, high 3rd party damage)
Note on J5: A = Highly improbable (has not been known to happen in rowing) B = Improbable (has been known to happen in rowing) C = Possible (could happen to about 1% of the competitors each decade) D = Probable (could happen to about 1% of the competitors each year) E = Highly probable (could happen to about 10% of the competitors each year)

## Matrix
|  | People | Assets | Probability
|  |  |  | A | B | C | D | E
|  |  |  | Highly improbable (has not been known to happen in rowing) | Improbable (has been known to happen in rowing) | Possible (could happen to about 1% of the club's active members per decade) | Probable (could happen to about 1% of the club's active members per year) | Highly probable (could happen to about 10% of the club's active members per year)
Severity | 1 | Slight injury or health effect (Requires little or no treatment; no need to take time off rowing or training) | Minor damage to equipment (<£100) | Low | Low | Low | Low | Moderate
| 2 | Minor injury or health effect (Requires First Aid or rest; potentially a few days off rowing or training) | Damage repair costs low (£500) | Low | Low | Low | Moderate | Substantial
| 3 | Moderate injury or health effect (Requires treatment beyond simple First Aid; potentially a week or so off rowing or training) | High damage repair costs (>£1000) | Low | Low | Moderate | Substantial | Intolerable
| 4 | Major injury or health effect (Requires hospital treatment for more than one day; potentially a few weeks off rowing or training) | Very high damage repair costs (loss of boat, 3rd party damage) | Low | Moderate | Substantial | Intolerable | Intolerable
| 5 | Fatality or Life Threatening Injury or Health Effect (could end a rowing career or cause hospitalisation for a few months) | Major damage & major costs (loss of several boats, high 3rd party damage) | Moderate | Substantial | Intolerable | Intolerable | Intolerable
|  | Low | An acceptable level of risk. No additional barriers/controls are required. Start or continue the activity but check that the current barriers/controls remain effective.
|  | Moderate | An acceptable level of risk that should be reviewed. Implement additional barriers/controls to reduce the risk if the opportunity arises. Start or continue the activity with care.
|  | Substantial | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced.
|  | Intolerable | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced. Prohibit the activity if it is not possible to reduce the risk.

## Sheet1 (hidden)
1 | A | Phone to summon assistance | Map showing navigation rules in boathouse | X | Launch | Ensure that rowers are always accompanied by the coaching launch
2 | B | Navigation rules | Enforce procedure to carry mobile phone in waterproof carrier |  | Capsize drill | Ensure capsize drills are run at the start of each season as a minimum. Keep a record
3 | C | Cox, bow steer competence | Club registration of coxes and bow steers competence |  | Steering competence | Ensure rowers become approved steers by passing the steering assessment.
4 | D | Club rescue launch | Ensure club rescue launch and crew are on the water or available and ready to boat at all times |  | Coaching | Ensure that rowers are coached in the correct handling of less stable boats
5 | E
1A | Low
1B | Low
1C | Low
1D | Low
1E | Moderate
2A | Low
2B | Low
2C | Low
2D | Moderate
2E | Substantial
3A | Low
3B | Low
3C | Moderate
3D | Substantial
3E | Intolerable
4A | Low
4B | Moderate
4C | Substantial
4D | Intolerable
4E | Intolerable
5A | Moderate
5B | Substantial
5C | Intolerable
5D | Intolerable
5E | Intolerable

## Colour key
Low | An acceptable level of risk. No additional barriers/controls are required. Start or continue the activity but check that the current barriers/controls remain effective.
Moderate | An acceptable level of risk that should be reviewed. Implement additional barriers/controls to reduce the risk if the opportunity arises. Start or continue the activity with care.
Substantial | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced.
Intolerable | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced. Prohibit the activity if it is not possible to reduce the risk.